## Effort by Task
| Task Duration | Person-months / month | Person-months | Work Package Person-months | CMU-Africa | Wits
WP1: Robot Acceptance Factors |  |  |  | 9.75
Task 1.1 ﻿South African Cultural Knowledge Survey | 3 | 1 | 3 |  |  | 3
Task 1.1 Rwandan Cultural Knowledge Survey | 3 | 1 | 3 |  | 3
Task 1.2 ﻿African Modes of Social Interaction | 3 | 0.5 | 1.5 |  |  | 1.5
Task 1.3 ﻿Africa-centric Design Patterns | 3 | 0.5 | 1.5 |  |  | 1.5
Task 1.4 ﻿Use Case Feedback | 3 | 0.25 | 0.75 |  |  | 0.75
WP2﻿ Interaction Scenario Specification |  |  |  | 3.25
Task 2.1 ﻿Use Case Scenario Definition | 3 | 0.5 | 1.5 |  | 1.5
Task 2.2 ﻿Robot Behavior Specification | 2 | 0.25 | 0.5 |  | 0.5
Task 2.3 ﻿Visitor Behavior Specification | 2 | 0.25 | 0.5 |  | 0.5
Task 2.3 ﻿Use Case Feedback | 3 | 0.25 | 0.75 |  |  | 0.75
WP3 ﻿ Systems Engineering |  |  |  | 16.95
Task 3.1 ﻿System Architecture Design | 7 | 0.5 | 3.5 |  | 3.5
Task 3.2 ﻿Software Engineering Standards | 3 | 0.25 | 0.75 |  | 0.75
Task 3.3 ﻿Software Installation | 35 | 0.1 | 3.5 |  | 3.5
Task 3.4 ﻿System Integration & Quality Assurance Manual | 35 | 0.1 | 3.5 |  | 3.5
Task 3.5 ﻿System Integration & Quality Assurance | 27 | 0.1 | 2.7 |  | 2.7
Task 3.6 ﻿Use Case Feedback | 3 | 1 | 3 |  | 3
WP4 ﻿Robot Sensing |  |  |  | 30.5
Task 4.1 ﻿Sensor Tests | 4 | 0.5 | 2 |  | 2
Task 4.2 ﻿Sensing & Analysis
Task 4.2.1 ﻿People Detection and Localization | 6 | 0.5 | 3 |  | 3
Task 4.2.2 ﻿Face & Eye Detection and Localization} | 6 | 0.5 | 3 |  | 3
Task ﻿4.2.3 Sound Detection and Localization | 6 | 0.5 | 3 |  | 3
﻿Rask 4.2.4 Robot Localization | 9 | 0.5 | 4.5 |  | 4.5
﻿Task 4.2.5 Camera Calibration | 3 | 0.5 | 1.5 |  |  | 1.5
﻿Task 4.3 Detection of Interaction of Events
﻿Task 4.3.1 Tablet PC Event | 9 | 0.5 | 4.5 |  |  | 4.5
﻿Task 4.3.2 Speech Event | 9 | 0.5 | 4.5 |  | 4.5
﻿Task 4.4 Use Case Feedback | 9 | 0.5 | 4.5 |  | 4.5
WP5 SRobot Behaviors |  |  |  | 43.5
﻿Task 5.1 Actuator Tests | 4 | 0.5 | 2 |  | 2
﻿Task 5.2 Animate Behavior Subsystem} | 5 | 0.5 | 2.5 |  | 2.5
﻿Task 5.3 Attention Subsystem | 9 | 0.5 | 4.5 |  | 4.5
﻿Task 5.4 Interaction Manager Subsystem
﻿Task 5.4.1 Cultural Knowledge Ontology & Knowledge Base | 9 | 0.5 | 4.5 |  |  | 4.5
﻿Task 5.4.2 Scenario Script Language | 6 | 0.5 | 3 |  |  | 3
﻿Task 5.4.3 Scenario Script Interpreter | 6 | 0.75 | 4.5 |  |  | 4.5
﻿Task 5.5 Gesture, Speech, & Navigation Subsystem
﻿Task 5.5.1 Gesture Execution | 12 | 0.5 | 6 |  | 6
﻿Task 5.5.2 Text to Speech Conversion | 6 | 0.5 | 3 |  |  | 3
﻿Task 5.5.3 Environment Map Generation | 9 | 0.5 | 4.5 |  | 4.5
﻿Task 5.5.4 Robot Navigation | 9 | 0.5 | 4.5 |  | 4.5
﻿Task 5.6 Use Case Feedback | 9 | 0.5 | 4.5 |  | 4.5
WP6 Use Case Evaluation |  |  |  | 4.5
Task 6.1 Use case implementation | 3 | 0.5 | 1.5 |  |  | 1.5
Task 6.2 Use case evaluation | 3 | 0.5 | 1.5 |  |  | 1.5
Task 6.3 Use case re-evaluation | 3 | 0.5 | 1.5 |  |  | 1.5
WP7 Dissemination and Impact |  |  |  | 6
Task 7.1 Online presence | 36 | 0.05 | 1.8 |  | 1.8
Task 7.2 Dissemination activities | 36 | 0.05 | 1.8 |  |  | 1.8
Task 7.3 Open-source software | 18 | 0.05 | 0.9 |  | 0.9
Task 7.4 Summer school | 3 | 0.5 | 1.5 |  |  | 1.5
WP8 Project Management |  |  |  | 8.4
Task 8.1 Project coordination | 36 | 0.05 | 1.8 |  | 1.8
Task 8.2 Administration | 36 | 0.05 | 1.8 |  | 1.8
Task 8.3 Risk management | 36 | 0.05 | 1.8 |  |  | 1.8
Task 8.4 Consortium agreement | 3 | 0.5 | 1.5 |  |  | 1.5
Task 8.5 Gender action plan | 3 | 0.5 | 1.5 |  |  | 1.5
Person-months |  |  | 122.85 | 122.85 | 81.75 | 41.1
Person-years |  |  | 10.2375 | 10.2375 | 6.8125 | 3.425