## Guidelines
Guidelines for the SoW Inclusive and Digital Transformation Grant Projects
A-What you need to know before completing the following SoW
1 | This SoW is a project planning tool that illustrates the timing of tasks and activities required to complete a project. The purpose is for high-level visibility about progress on the key areas of your project and not about detailed project managment. Break your project down into high-level Tasks to be completed. A typical project might have 5 to 10 tasks. If you have in mind many more tasks than this, please consider combining them. In turn, each task should be broken down into specific activities. A typical task might have 5 to 10 activities. Note that only one partner university can be assigned to each activity. So, if several partners are working together on something, each partner will have its own activity and description of how they are contributing to its completion and success.
B- Please complete the information in the Project Information and SoW tabs

## Project Information
Project Information
Project Name: |  | Culturally Sensitive Social Robotics for Africa (CSSR4Africa)
Start Date: |  | 2023-07-01
End Date: |  | 2025-06-30
Contact information for each University working on this project
|  | Name of researcher | Phone number | Email | Name of University | Briefly describe the role of this university in the project < 50 words each
| 1 | Dr. Pravesh Ranchod |  | Pravesh.Ranchod@wits.ac.za | University of the Witwatersrand | Overall responsibility for Task ...
| 2 | Prof. Benjamin Rosman |  | Benjamin.Rosman1@wits.ac.za | University of the Witwatersrand | Overall responsibility for Task ...
| 3 | Prof. David Vernon | 00250 785927470 | vernon@cmu.edu | Carnegie Mellon University Africa | Overall responsibility for Task 2 Interaction Scenario Specification, Task 3 Systems Engineering, Task 5 Robot Behaviors, Task 8 Project Management.
| Project Abstract: (250 words max) | The objectives of the CSSR4Africa project are (i) to identify the verbal and non-verbal social and cultural norms of human interaction that are prevalent in countries in Africa, (ii) to encapsulate them in the behavioral patterns of social robots so that they can engage with African people in a manner that is consistent with their expectations of acceptable social interaction, and (iii) to demonstrate these culturally-sensitive social robot behaviors in two use cases: one for giving a tour of a university laboratory, and one for assisting and giving directions to visitors at the reception of a university. In order to ensure that the project objectives can be achieved in the time available, we restrict the scope of the project to the cultures and social practices that are prevalent in Rwanda and South Africa.
List and description of project tasks
| Task ID | Task / Outcome Name | Task / Outcome Description (< 50 words for each Task) |  |  | Indicator(s) Task / Outcome has been Achieved
| Task1: | African Cultural Knowledge | Identify the knowledge that is required to effect culturally-sensitive interaction in Rwanda and South Africa. Use this cultural knowledge to identify, adjust, and augment the spatial, non-verbal, and verbal modes of interaction that impact the effectiveness of human-robot interaction, and adapt and augment the eight design patterns for sociality. |  |  | Deliverables D1.1 - D1.4, as specified in the project work plan (https://cssr4africa.github.io/workplan).
| Task2: | Interaction Scenario Specification | Develop the two use case scenarios and define detailed procedures for their execution. Specify the desired robot behavior and the expected visitor behavior, i.e., the expected interactions by the person to whom the tour is being given or by the person at reception. |  |  | Deliverables D2.1 - D2.4, as specified in the project work plan (https://cssr4africa.github.io/workplan).
| Task3: | Systems Engineering | Design a software architecture that will facilitate the integration of the results of the project into a complete operational culturally sensitive social robotics system. Formalize the integration process by identifying appropriate software engineering standards and quality assurance procedures. Carry out this integration and quality assurance process. |  |  | Deliverables D3.1 - D3.6, as specified in the project work plan (https://cssr4africa.github.io/workplan).
| Task4: | Robot Sensing | Develop a suite of sensor unit tests. Identify and implement algorithms that will detect and localize people, including their face and eyes, localize sounds, and localize the robot in a world frame of reference. Detect interaction events on the robot’s tablet PC. Detect speech events and perform automated speech recognition. |  |  | Deliverables D4.1, D4.2.1 - D4.2.5, D4.3.1 - D4.3.2 as specified in the project work plan (https://cssr4africa.github.io/workplan).
| Task5: | Robot Behaviors | Develop a suite of actuator unit tests. Develop an animate behavior subsystem. Develop an attention subsystem. Develop an interaction manager subsystem to control robot interaction with a human partner, exhibiting culturally sensitive behaviors appropriate for the use case scenarios. Develop a subsystem for robot gestures, speech, and navigation. |  |  | Deliverables D5.1, D5.2, D5.3, D5.4.1 - D5.4.3, D5.5.1 - D5.5.4, as specified in the project work plan (https://cssr4africa.github.io/workplan).
| Task6: | Use Case Evaluation | Carry out initial demonstrations of the system architecture in the two use cases. Evaluate the success of the demonstrations and identify any adjustments to the output from Tasks 1 - 5. Carry out final demonstrations. Re-evaluate the success of the demonstrations. |  |  | Deliverables D6.1 - D6.3, as specified in the project work plan (https://cssr4africa.github.io/workplan).
| Task7: | Dissemination and Impact | Create a project website. Disseminate the ongoing status of the project in several forums, including the project website. Publish research results in conferences and journals. Make the project software and data freely available online. Organize a summer school. |  |  | Deliverables D7.1 - D7.4, as specified in the project work plan (https://cssr4africa.github.io/workplan).
| Task8: | Project Management | Carry out coordination, finance, and management activities. Prepare and sign a consortium agreement. Prepare and execute a gender action plan. |  |  | Deliverables D8.1 - D8.4, as specified in the project work plan (https://cssr4africa.github.io/workplan).

## SOW
Statement of work for Inclusive and Digital Transformation Grant Projects |  |  |  |  | Project SoW for a Three-Year Grant
Project Name: | Culturally Sensitive Social Robotics for Africa (CSSR4Africa) |  |  |  | Approx. Timing Please mark approximate timing with a Black "X"
Start Date: | 2023-07-01
End Date: | 2025-06-30 |  |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| Activity ID | Activity Name | Brief description (<25 words) | Target indicators for activity | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Responsible University
Task/Outcome 1 | African Cultural Knowledge
| 1.1 | South African Cultural Knowledge Survey. | Carry out an ethnographic study with the goal of identifying the knowledge that is required to effect culturally-sensitive interaction in Rwanda and South Africa. | Deliverable D1.1 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q1 to Year 1 Q2
| 1.1 | Rwandan Cultural Knowledge Survey. | Carry out an ethnographic study with the goal of identifying the knowledge that is required to effect culturally-sensitive interaction in Rwanda and South Africa. | Deliverable D1.1 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 1 Q2
| 1.2 | African Modes of Social Interaction. | Adjust or augment the spatial, non-verbal, and verbal modes of interaction that impact the effectiveness of human-robot interaction in Africa by incorporating cultural knowledge. | Deliverable D1.2 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q3
| 1.3 | Africa-centric Design Patterns. | Adapt and augment the design patterns for sociality in human-robot interaction by incorporating cultural knowledge. | Deliverable D1.3 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q3
| 1.4 | Use Case Feedback. | Update the African cultural knowledge, Africa-centric modes of interaction, and Africa-centric design patterns for sociality based on feedback from the use case evaluations. | Deliverable D1.4 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 3 Q1
Task/Outcome 2 | Interaction Scenario Specification
| 2.1 | Use Case Scenario Definition. | Define the two use cases: lab tour guide and receptionist. | Deliverable D2.1 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 1 Q2
| 2.2 | Robot Behavior Specification. | Generate a list of desired robot behaviors, i.e., sequences of actions, that the gesture, speech, and navigation subsystem in Task 5 will later synthesize. | Deliverable D2.2 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q2
| 2.3 | Visitor Behavior Specification. | Specify the visitor’s interaction behaviors that will be facilitated in the use case scenarios. | Deliverable D2.3 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q2
| 2.4 | Use Case Feedback. | Update the use cases based on feedback from the use case evaluations. | Deliverable D2.4 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 3 Q1
Task/Outcome 3 | Systems Engineering
| 3.1 | System Architecture Design. | Design the system architecture to integrate the functionality developed in Tasks 4 and 5, providing the necessary infrastructure to implement each of the two use cases. | Deliverable D3.1 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 1 Q3
| 3.2 | Software Engineering Standards. | Define a set of project standards governing the specification, design, documentation, and test of all software to be developed in Tasks 4 and 5. | Deliverable D3.2 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1
| 3.3 | Software Installation. | Document the process for the installation and execution of the software required to instantiate all or part of the CSSR4Africa system. | Deliverable D3.3 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 3 Q4
| 3.4 | System Integration & Quality Assurance Manual. | Write a manual specifying the procedures to be followed when developing software in the project, submitting it for integration into the current system release. | Deliverable D3.4 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q2 to Year 1 Q3
| 3.5 | System Integration & Quality Assurance. | Incorporate software submitted for integration in the current version of the CSSR4Africa system. | Deliverable D3.5 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q4 to Year 3 Q4
| 3.6 | Use Case Feedback. | Update the system architecture based on feedback from the use case evaluations. | Deliverable D3.6 (*). | [12 empty] | Carnegie Mellon University | bar: Year 3 Q1
Task/Outcome 4 | Robot Sensing
| 4.1 | Sensor Tests. | Write a suite of unit tests, one for each sensor, to verify that sensor data is successfully acquired on each sensor topic. | Deliverable D4.1 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 1 Q2
| 4.2 | People Detection and Localization. | Develop a software module to detect and localize people in the robot’s field of view. | Deliverable D4.2.1 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 1 Q2
| 4.3 | Face & Eye Detection and Localization. | Develop a software module to detect and localize the faces and eyes of people in the robot’s field of view. | Deliverable D4.2.2 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 1 Q2
| 4.4 | Sound Detection and Localization. | Develop a software module to detect and identify the direction of arrival of a conspicuous sound within the robot’s hearing range. | Deliverable D4.2.3 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 1 Q2
| 4.5 | Robot Localization. | Develop a software module to determine the pose (*) of the robot in a Cartesian world frame of reference. | Deliverable D4.2.4 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q3 to Year 2 Q1
| 4.6 | Camera Calibration. | Develop a software module to determine the 3×4 camera model matrix for the robot’s top forward facing camera and depth RGB-D camera. | Deliverable D4.2.5 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q2
| 4.7 | Tablet PC Event. | Develop a software module that implements the state transition diagram developed in Activity 2.3 capturing the visitor interactions with the robot’s tablet PC. | Deliverable D4.3.1 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q3 to Year 2 Q1
| 4.8 | Speech Event. | Train, test, and deploy a speech-to-text model for detecting utterances made by an interaction partner in the language of Kinyarwanda and transcribing them into written text. | Deliverable D4.3.2 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q3 to Year 2 Q1
| 4.9 | Use Case Feedback. | Update the robot sensing based on feedback from the use case evaluations. | Deliverable D4.4 (*). | [12 empty] | Carnegie Mellon University | bar: Year 3 Q1 to Year 3 Q3
Task/Outcome 5 | Robot Behaviors
| 5.1 | Actuator Tests. | Write a suite of unit tests, one for each actuator, to verify that every actuator can be controlled successfully using ROS. | Deliverable D5.1 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 1 Q2
| 5.2 | Animate Behavior Subsystem. | Develop a software module to give the robot the appearance of an animate agent by making subtle body movements. | Deliverable D5.3 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q2 to Year 1 Q3
| 5.3 | Attention Subsystem. | Develop a software module to allow the robot to pay attention to salient features in its environment. | Deliverable D5.3 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q3 to Year 2 Q1
| 5.4 | Cultural Knowledge Ontology & Knowledge Base. | Formulate a cultural knowledge ontology and use it to create a knowledge base formalizing the culturally sensitive knowledge that are documented in Deliverables D1.2 and D1.3. | Deliverable D5.4.1 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q4 to Year 2 Q2
| 5.5 | Scenario Script Language. | Define a language that can be used to capture the interactions in the use case scenarios and enact them using the cultural knowledge ontology and cultural knowledge base. | Deliverable D5.4.2 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q3 to Year 1 Q4
| 5.6 | Scenario Script Interpreter. | Develop an interpreter for the scenario script language defined in Deliverable D5.4.2. | Deliverable D5.4.3 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 2 Q1 to Year 2 Q2
| 5.7 | Gesture Execution. | ﻿Develop a software module that enables the Pepper robot to execute body and hand gestures. | Deliverable D5.5.1 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q2 to Year 2 Q1
| 5.8 | English Text to Speech Conversion. | Implement a text to speech facility that will allow the Pepper robot to communicate with humans using spoken English. | Deliverable D5.5.2.1 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q3 to Year 1 Q4
| 5.9 | isiZulu Text to Speech Conversion. | Implement a text to speech facility that will allow the Pepper robot to communicate with humans using spoken isiZulu. | Deliverable D5.5.2.2 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q3 to Year 1 Q4
| 5.1 | Kinyarwanda Text to Speech Conversion. | Implement a text to speech facility that will allow the Pepper robot to communicate with humans using spoken Kinyrwanda. | Deliverable D5.5.2.3 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q3 to Year 1 Q4
| 5.1 | Integrated Text to Speech Conversion. | Implement a text to speech facility that will allow the Pepper robot to communicate with humans using spoken English, isiZulu, and Kinyrwanda. | Deliverable D5.5.2.4 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q3 to Year 1 Q4
| 5.11 | Environment Map Generation. | ﻿Develop a software module to generate a metric map of the environments that will be used in the two use case scenarios documented in Deliverable D2.1. | Deliverable D5.5.3 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 1 Q3
| 5.12 | Robot Navigation. | ﻿Develop a software module to control the locomotion of the Pepper robot so that it can navigate in its environment, comprising fixed inanimate obstacles and humans. | Deliverable D5.5.4 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q4 to Year 2 Q2
| 5.13 | Use Case Feedback. | Update the robot behaviors based on feedback from the use case evaluations. | Deliverable D5.6 (*). | [12 empty] | Carnegie Mellon University | bar: Year 3 Q1 to Year 3 Q3
Task/Outcome 6 | Use Case Evaluation
| 6.1 | Use Case Implementation. | Implement both use cases using the outcomes of Tasks 1 - 5, i.e., the cultural knowledge, the scenario specification, and the integrated robot’s sensory and interaction capabilities. | Deliverable D6.1 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 2 Q3
| 6.2 | Use Case Evaluation. | Evaluate the implementation using the Robot Social Attribute Scale (*) and produce a set of required adjustments for the interaction primitives and design patterns. | Deliverable D6.2 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 2 Q4
| 6.3 | Use Case Re-Evaluation. | Re-evaluate the implementation after completing the adjustments in Tasks 1 --5, arising from the evaluation in Activity 6.2. | Deliverable D6.3 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 3 Q4
Task/Outcome 7 | Dissemination and Impact
| 7.1 | Online Presence. | ﻿Communicate project aims and results to the general public and stakeholders. | Deliverable D7.1 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 3 Q4
| 7.2 | Dissemination Activities. | ﻿Effect scientific dissemination through leading international conferences and journals, as well as through forums such as AI Saturdays, Knowledge for All, and AI4D. | Deliverable D7.2 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q1 to Year 3 Q4
| 7.3 | Open-Source Software Repository. | Make software, data, and protocols publicly available on GitHub and maintain the repositories. | Deliverable D7.3 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q2 to Year 3 Q4
| 7.4 | Summer School. | ﻿Organize a summer school on culturally-sensitive human-robot interaction in 2026. | Deliverable D7.4 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 3 Q4
Task/Outcome 8 | Project Management
| 8.1 | Project Coordination. | ﻿Coordinate the technical work in the project. Monitor progress and take appropriate timely action. Organize periodic meetings and write periodic progress reports. | Deliverable D8.1 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 3 Q4
| 8.2 | Administration. | Plan and monitor financial expenditure, and submit periodic financial reports. | Deliverable D8.2 (*). | [12 empty] | Carnegie Mellon University | bar: Year 1 Q1 to Year 3 Q4
| 8.3 | Risk Management. | Monitor identified risks, and take appropriate corrective actions, where necessary. Monitor the possible emergence of new risks and updates the risk plan accordingly. | Deliverable D8.3(*).. | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q1 to Year 3 Q4
| 8.4 | Consortium Agreement. | Draft a consortium agreement setting out the rights and obligations of the partners, addressingIPR and the adoption of an appropriate open source licence. | Deliverable D8.4(*).. | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q1 to Year 1 Q2
| 8.5 | Gender Action Plan. | ﻿Draft a gender action plan with the specific intent of ensuring there is no gender bias in any activity directed at stakeholders. | Deliverable D8.5 (*). | [12 empty] | University of the Witwatersrand. | bar: Year 1 Q1 to Year 1 Q2
(*) See https://cssr4africa.github.io/workplan.

## Sheet2 (hidden)
Partner Universities
University of Ghana
Cairo University
Université Jean Lorougnon Guede
Université Cheikh Anta Diop
Dedan Kimathi University of Technology
Makerere University
University of Pretoria
University of Nairobi
University of Lagos
University of Rwanda
Carnegie Mellon University
American University in Cairo
Carnegie Mellon University Africa.
University of the Witwatersrand.